## Settings
Settings
Gantt
Project Details |  |  | Project Role Types |  |  |  | Project Team |  |  |  | Non working day |  |  | Non working day (Filtered) |  |  |  |  | Stages
| Project Title: | Example Project |  | Role | Code | # |  | Name | Role | Code |  | Description | Date |  | Filter 1 | F. Edward | ✔ | Filter 5 |  | Stages
|  |  |  | Project Management | PM | 1 |  | F. Edward | Project Management | PM |  | Holiday 1 | 2021-10-20 |  | Filter 2 | G. Billy | ✔ | Filter 6 |  | Plan
| Project Manager: | F.Edward |  | Coding | COD | 3 |  | G. Billy | Coding | COD |  | Holiday 2 | 2021-11-04 |  | Filter 3 | E. John | ✔ | Filter 7 |  | Implementation
|  |  |  | Design | DES | 1 |  | Z. Mark | Coding | COD |  |  |  |  | Filter 4 |  |  | Filter 8 |  | Rollout prep
| Project Priority: | High |  | Marketing | MAR | 1 |  | E. John | Design | DES | [9 empty] | Rollout
|  |  |  | Finance | FIN | 1 |  | J. Steven | Finance | FIN |  |  |  |  | Description | Date | Filtered | Filtered |  | Test
[8 empty] | M. Yun | Coding | COD |  |  |  |  | F. Edward | 2021-11-24 | 2021-11-24 | 2021-11-24 |  | Release
[8 empty] | C. Timmy | Marketing | MAR |  |  |  |  | G. Billy | 2021-11-12 | 2021-11-12 | 2021-11-12
[15 empty] | E. John | 2021-10-27 | 2021-10-27 | 2021-10-27
* Maximum 14 roles
Formulas:
Filtered = IF(OR(AND(AA8="✔",[Filter 1]=Z8),AND(AA9="✔",[Filter 1]=Z9),AND(AA10="✔",[Filter 1]=Z10),AND(AA11="✔",[Filter 1]=Z11),AND(AD8="✔",[Filter 1]=AC8),AND(AD9="✔",[Filter 1]=AC9),AND(AD10="✔",[Filter 1]=AC10),AND(AD11="✔",[Filter 1]=AC11)),[F. Edward],"")

## Gantt
Example Project
[21 empty] | Project Timespan: | [7 empty] | 2021-05-14 |  |  |  | - | 2021-12-01 |  |  |  | (202) |  |  |  |  | Project Manager: | [6 empty] | F.Edward | [10 empty] | Settings
|  | Input Column | [18 empty] | Colour By | [8 empty] | Display | [8 empty] | Show Progress | [21 empty] | Highlight
|  | Calculated Column | [18 empty] | Team Roles | [8 empty] | Plan | [8 empty] | Yes | [21 empty] | 2021-10-21
Snapshot Column
[20 empty] | Week | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27
| ⚠ - ◆ - 🏴 - ↖ - ↙ | [6 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11
[8 empty] | Update on: | [9 empty] | Saved on: |  | 17
ids |  |  | Items Details |  |  |  |  | 2021-05-03 | [9 empty] | 2021-05-03
id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. Item |  | d. conn | d. lag | Work days | Start | End | Start | End | % | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | 1 | -1 | S | Planning |  |  | ⚠ | 2021-05-14 |  |  | FALSE |  | FS |  | 15 | 2021-05-14 | 2021-05-28 | 2021-05-10 | 2021-05-20 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 1 | T | Task P1 | PM | F. Edward | ⚠ | 2021-05-14 |  |  | FALSE |  | FS |  | 10 | 2021-05-14 | 2021-05-23 | 2021-05-10 | 2021-05-13 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 2 | T | Task P2 | COD | G. Billy |  |  |  | 2 | ↖ | (T) Task P1 | FS | 0 | 4 | 2021-05-24 | 2021-05-27 | 2021-05-14 | 2021-05-18 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 2 | T | Task P3 | COD | Z. Mark | ⚠ |  |  | 3 | ↖ | (T) Task P2 | FS | -1 | 2 | 2021-05-27 | 2021-05-28 | 2021-05-19 | 2021-05-20 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | 1 | M | Milestone I | PM | F. Edward | ⚠ |  |  | 4 | ↖ | (T) Task P3 | FF |  |  | 2021-05-28 | 2021-05-28 | 2021-05-20 | 2021-05-20 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | -1 | S | Implementation |  |  |  | 2021-05-29 |  |  | FALSE |  | FS |  | 10 | 2021-05-29 | 2021-06-07 | 2021-05-21 | 2021-06-03 | 65% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2 | 3 | T | Task l1 | DES | E. John |  |  |  | 1 | ↖ | (S) Plannin…. | FS |  | 5 | 2021-05-29 | 2021-06-02 | 2021-05-21 | 2021-05-27 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | 5 | T | Task l2 | FIN | J. Steven |  |  |  | 7 | ↖ | (T) Task l…. | FS |  | 3 | 2021-06-03 | 2021-06-05 | 2021-05-28 | 2021-06-01 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | 2 | T | Task l3 | COD | Z. Mark |  |  |  | 8 | ↖ | (T) Task l…. | FS |  | 2 | 2021-06-06 | 2021-06-07 | 2021-06-02 | 2021-06-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2 | 5 | M | Milestone II | FIN | J. Steven |  |  |  | 9 | ↖ | (T) Task l…. | FF |  |  | 2021-06-07 | 2021-06-07 | 2021-06-03 | 2021-06-03 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3 | -1 | S | Rollout Prep |  |  |  | 2021-05-28 |  |  | FALSE |  | FS |  | 11 | 2021-05-28 | 2021-06-07 | 2021-05-20 | 2021-06-03 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3 | 5 | T | Task RP1 | FIN | J. Steven |  |  |  | 13 | ↙ | (T) Task RP…. | SF |  | 5 | 2021-05-28 | 2021-06-01 | 2021-05-20 | 2021-05-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | 2 | T | Task RP2 | COD | Z. Mark |  |  |  | 14 | ↙ | (T) Task RP…. | SF |  | 4 | 2021-06-02 | 2021-06-05 | 2021-05-27 | 2021-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3 | 4 | T | Task RP3 | MAR | C. Timmy |  |  |  | 15 | ↙ | (M) Milesto…. | FF |  | 2 | 2021-06-06 | 2021-06-07 | 2021-06-02 | 2021-06-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3 | 1 | M | Milestone III | PM | F. Edward |  |  |  | 6 | ↖ | (S) Impleme…. | FF |  |  | 2021-06-07 | 2021-06-07 | 2021-06-03 | 2021-06-03 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 4 | -1 | S | Rollout |  |  |  | 2021-06-08 |  |  | FALSE |  | FS |  | 9 | 2021-06-08 | 2021-06-16 | 2021-06-04 | 2021-06-16 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 4 | -1 | T | Task R1 | [5 empty] | 11 | ↖ | (S) Rollout…. | FS |  | 3 | 2021-06-08 | 2021-06-10 | 2021-06-04 | 2021-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 4 | -1 | T | Task R2 | [5 empty] | 17 | ↖ | (T) Task R1 | FS |  | 3 | 2021-06-11 | 2021-06-13 | 2021-06-09 | 2021-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 4 | -1 | T | Task R3 | [5 empty] | 18 | ↖ | (T) Task R2 | FS |  | 3 | 2021-06-14 | 2021-06-16 | 2021-06-14 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 4 | -1 | M | Milestone IV | [5 empty] | 19 | ↖ | (T) Task R3 | FF |  |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 5 | -1 | S | Test |  |  |  | 2021-10-20 |  |  | FALSE |  | FS |  | 30 | 2021-10-20 | 2021-11-18 | 2021-10-20 | 2021-11-18 | 65% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 5 | 2 | T | Task T1 | COD | G. Billy |  | 2021-10-20 |  |  | FALSE |  | FS |  | 10 | 2021-10-20 | 2021-10-29 | 2021-10-20 | 2021-10-29 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 5 | 2 | T | Task T2 | COD | Z. Mark |  |  |  | 22 | ↖ | (T) Task T1 | FS |  | 10 | 2021-10-30 | 2021-11-08 | 2021-10-31 | 2021-11-09 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 5 | 2 | T | Task T3 | COD | Z. Mark |  |  |  | 23 | ↖ | (T) Task T2 | FS |  | 10 | 2021-11-09 | 2021-11-18 | 2021-11-09 | 2021-11-18 | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 5 | 4 | T | Task T4 | MAR | C. Timmy |  |  |  | 26 | ↙ | (M) Milesto…. | FF |  | 10 | 2021-11-09 | 2021-11-18 | 2021-10-25 | 2021-11-04 | 70% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 5 | 1 | M | Milestone V | PM | F. Edward |  | 2021-11-18 |  |  | FALSE |  | FS |  |  | 2021-11-18 | 2021-11-18 | 2021-11-04 | 2021-11-04 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 6 | -1 | S | Test 2 |  |  |  | 2021-11-01 |  |  | FALSE |  |  |  | 7 | 2021-11-01 | 2021-11-07 | 2021-11-04 | 2021-11-04 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 6 | 2 | T | Task T1 | COD | G. Billy |  | 2021-11-01 |  |  | FALSE |  |  |  | 4 | 2021-11-01 | 2021-11-04 | 2021-11-01 | 2021-11-04 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 6 | 3 | T | Task T2 | DES | E. John |  |  |  | 28 | ↖ | (T) Task T1 | FS |  | 3 | 2021-11-05 | 2021-11-07 | 2021-11-05 | 2021-11-07 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 6 | 3 | M | Milestone VI | DES | E. John |  |  |  | 29 | ↖ | (T) Task T2 | FF |  |  | 2021-11-07 | 2021-11-07 | 2021-11-07 | 2021-11-07 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 7 | -1 | S | Test 3 |  |  |  | 2021-11-01 |  |  | FALSE |  | FF |  | 31 | 2021-11-01 | 2021-12-01 | 2021-11-01 | 2021-12-01 | 98% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 7 | 5 | T | Task T1 | FIN | J. Steven |  | 2021-11-01 |  | 30 | ↖ | (M) Milesto…. | FF |  | 31 | 2021-11-01 | 2021-12-01 | 2021-11-01 | 2021-12-01 | 98% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 7 | 2 | M | Milestone VI | COD | Z. Mark |  |  |  | 32 | ↖ | (T) Task T1 | FF |  |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | -1 | -1 | [8 empty] | FALSE | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Colour By = WEEKNUM([Colour By, row below],21)

## .
Github link for more update
edward-0116/UltiExcelGantt: Ultimate Excel Gantt Chart (github.com)
I spent 4 hours of my weekend time to create this Gantt chart by following Youtube link below.
Credit to original developer.
https://www.youtube.com/watch?v=OizqFlMtZLQ&ab_channel=TheOfficeLab
https://excelfind.com/excel_templates/ultimate-excel-gantt-chart/
Spent another countless hours to add more features to make this Gantt chart to be more viable.
Feel free to buy me a cup of coffee if you think this is helpful. 😁
Paypal: | https://paypal.me/FooYangYi?country.x=MY&locale.x=en_US
Developed with with Microsoft® Excel® for Microsoft 365 MSO (Version 2110 Build 16.0.14527.20270) 64-bit